## Sheet1
Bug ID | Description | Pre-requisite | Tests to Reproduce | Expected Result | Actual Result | Status | Executed By | Browser/Device | Attachments
B001 | Verify whether user able to login to his account after registration with emaid id and password | Open the url and enter the url : https://casioclone.netlify.app/pages/authentication/login | 1.Enter test data in input field 2.click the login button | User should successfully login | User got message Login successfully but its not login just redirected to hompage without login | FAIL | Sanket | Chrome(134.0.6998.178) | login bug
B002 | Verify whether user able to login to his account through facebook | Open the url and enter the url : https://casioclone.netlify.app/pages/authentication/login | 1.Enter facebook id and password in input field after clicking login with facebook | User should redirected to facebook login page | User not able to click the facebook option | FAIL | Sanket | Chrome(134.0.6998.178) | login bug
B003 | Verify whether user able to login to his account directly from Email | Open the url and enter the url : https://casioclone.netlify.app/pages/authentication/login | 1.Enter mail id and password in input field and its directly login | User should click the email and redirected to mail id page for directly login | User when click Email option "Google Sign-In Failed" displayed | FAIL | Sanket | Chrome(134.0.6998.178) | login bug
B004 | Verify whether user able to use forgot password functionality | Open the url and enter the url : https://casioclone.netlify.app/pages/authentication/login | 1.Click on Forgot Password 2.Give your mail or phone number 3. Receive rest link in mail/phone | User should be redirected to a page where site want a mail or phone number to send email link | User is not able to click forgot password option | FAIL | Sanket | Chrome(134.0.6998.178) | login bug
B005 | Verify whether user able to register his account with entering phone number More/less than 10 digits | Open the url and enter the url : https://casioclone.netlify.app/pages/authentication/signup | 1.Enter the test data in each input field. 2.Click on Register button. | User should get an error message to fill phone number field wrong | User registered the account | FAIL | Sanket | Chrome(134.0.6998.178) | Registration bug
B006 | Verify whether user able to register his account with entering Wrong Email ID | Open the url and enter the url : https://casioclone.netlify.app/pages/authentication/signup | 1.Enter the test data in each input field. 2.Click on Register button. | User should get an error message to fill correct Email id | User registered the account | FAIL | Sanket | Chrome(134.0.6998.178) | Registration bug
B007 | Verify whether user able to register his account with entering Password which is not match the criteria of password | Open the url and enter the url : https://casioclone.netlify.app/pages/authentication/signup | 1.Enter the test data in each input field. 2.Click on Register button. | User should get an error message that password doesn't meet criteria | User registered the account | FAIL | Sanket | Chrome(134.0.6998.178) | Registration bug
B008 | Verify whether user able to register his account with entering Password and confirm password different | Open the url and enter the url : https://casioclone.netlify.app/pages/authentication/signup | 1.Enter the test data in each input field. 2.Click on Register button. | User should get an error message to fill password correct | User registered the account | FAIL | Sanket | Chrome(134.0.6998.178) | Registration bug
B009 | Verify whether homepage product images are accessable or not | Open the url and enter the url : https://casioclone.netlify.app/ | 1.Enter homepage 2.Click on homepage product images | Website should open that product which product user clicks | Website is not responding its just product image no links attached | FAIL | Sanket | Chrome(134.0.6998.178) | Homepage Bug
B010 | Verify homepage some option after scrolling like "New Drops" | Open the url and enter the url : https://casioclone.netlify.app/ | 1.Enter homepage 2.Scrool down homepage some new drop product 3.Click on the product | Website should open that product which product user clicks | Website Showing "Page not found" after clicking | FAIL | Sanket | Chrome(134.0.6998.178) | Homepage Bug
B011 | Verify homepage some option after scrolling like "Topics" | Open the url and enter the url : https://casioclone.netlify.app/ | 1.Enter homepage 2.Scrool down homepage see Topics 3.Click on the Topic | Website should open Topics and product in the toipics | Website just refresh and back to Homepage | FAIL | Sanket | Chrome(134.0.6998.178) | Homepage Bug
B012 | Verify homepage some option after scrolling like "Product Category" | Open the url and enter the url : https://casioclone.netlify.app/ | 1.Enter homepage 2.Scrool down homepage and see product category 3.Click on the product category | Website should open the products listed in product category | Website just refresh and back to Homepage | FAIL | Sanket | Chrome(134.0.6998.178) | Homepage Bug
B013 | Verify the Footer section in website homepage | Open the url and enter the url : https://casioclone.netlify.app/ | 1.Enter homepage 2.Scrool down homepage and go to footer section 3.Click on any options | Website should open what i click e.g.. If i click social media open social media sites..... if i open policies open policies | Website just refresh and back to Homepage | FAIL | Sanket | Chrome(134.0.6998.178) | Homepage Bug
B014 | Verify homepage some option after scrolling like "View all New Drops" | Open the url and enter the url : https://casioclone.netlify.app/ | 1.Enter homepage 2.Scrool down homepage and select view all new drops button 3.Click on the button | User should see a new page with all products and the products are accessible | User seccussefully view a new page but products are not accessible | FAIL | Sanket | Chrome(134.0.6998.178) | Homepage Bug
B015 | Verify wishlist product | Open the url and enter the url : https://casioclone.netlify.app/pages/wishlist.html | 1. Add any product to wishlist 2. Product added to wishlist | User should successfully add some product to wishlist | Website show "Failed to get the wishlist" | FAIL | Sanket | Chrome(134.0.6998.178) | Wishlist bug
B016 | Verify "Watch" option from Navbar of the webpage | Open the url and enter the url : https://casioclone.netlify.app/ | 1. Open the watch option and select any watch | User click on any product user go to the view page of the product on the same site | When User select any product User redirected to main Casio Website | FAIL | Sanket | Chrome(134.0.6998.178) | Navbar Bug
B017 | Verify "Electronic Musical Instruments" option from Navbar of the webpage | Open the url and enter the url : https://casioclone.netlify.app/ | 1. Open the Electronic Musical Instruments option and select any Electronic Musical Instruments | User click on any product user go to the view page of the product on the same site | When User select any product User redirected to main Casio Website | FAIL | Sanket | Chrome(134.0.6998.178) | Navbar Bug
B018 | Verify "Calculators" option from Navbar of the webpage | Open the url and enter the url : https://casioclone.netlify.app/ | 1. Open the Calculators option and select any Calculator | User click on any product user go to the view page of the product on the same site | When User select any product User redirected to main Casio Website | FAIL | Sanket | Chrome(134.0.6998.178) | Navbar Bug
B019 | Verify "Label Printers & Others" option from Navbar of the webpage | Open the url and enter the url : https://casioclone.netlify.app/ | 1. Open the Label Printers & Others option and select any Label Printers | User click on any product user go to the view page of the product on the same site | User clicks the Label Printers & Others option nothing open | FAIL | Sanket | Chrome(134.0.6998.178) | Navbar Bug